## Sheet1
|  | 2021 | [11 empty] | 2022
Commitment | Key deliverables | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Ongoing consultation on strategy and plan | Publish strategy and inform stakeholders | bar: 2021 Jan; 2022 Dec
Digitalisation specific engagement events | bar: 2021 Jul to 2021 Sep; 2022 Jul to 2022 Sep
Receive and review feedback
2. Upgrade our core asset repository and finance systems | Complete future system design | bar: 2021 Jan to 2021 Feb
Build phase of new system | bar: 2021 Jan to 2021 Dec
Data migration | bar: 2021 Jan to 2021 Dec
Cutover to new system | bar: 2021 Oct to 2022 Feb
3. Digitise remaining asset data sets | Complete Service Governor surveys and digitisation programme | bar: 2021 Jan to 2021 Mar
Cathodic Protection Systems digitised and mapped to assets | bar: 2021 Apr to 2021 Aug
Multi-Occupancy Building (MOBs) moved from standalone databases to core asset repository | bar: 2021 Jan to 2021 Aug
4. Internet of Things (IoT) | Innovation project on trial sites to explore sensors, remote monitoring and remote maintenance technologies | bar: 2021 Apr to 2021 Dec
Develop a strategy and plan for sensors and monitoring | bar: 2021 Sep to 2022 Apr
Deliver phase 1 of the IoT plan | bar: 2022 May to 2022 Dec
Derive GD3 IoT plan | bar: 2022 Oct to 2022 Dec
5. Publish a metadata catalogue | Derive 1st catalogue based on stakeholder themes | bar: 2021 Jan to 2021 Mar
Publish on our website and inform stakeholders | bar: 2021 Apr
Publish further links to key data sets and analysis | bar: 2021 Apr; 2021 Oct to 2021 Nov; 2022 Apr to 2022 May; 2022 Oct to 2022 Nov
6 monthly review and update to metadata catalogue | bar: 2021 Oct to 2021 Nov; 2022 Apr to 2022 May; 2022 Oct to 2022 Nov
6. Pathfinder | Use of Pathfinder in a number of projects including:
Milford Haven Energy Kingdom - Innovate UK project | bar: 2021 Jan to 2021 Mar
West of England Combined Authority | bar: 2021 Feb to 2021 Dec
Zero 2050 - South Wales Decarbonisation planning | bar: 2021 Jan to 2021 Mar
| Zero 2050 - South Wales Decarbonisation roll out to the rest of Wales (dependency on Welsh Gov) | 2021 Jun: TBC
Gas Goes Green workstream 1.4 local, regional & mational pathways studies | bar: 2021 Jan to 2021 Oct
Engage on further projects and use cases
7. Priority Services Register (PSR) | Productionalise PSR data on maps to help plan projects | bar: 2021 Jan to 2021 Jul
Resolve GDPR issus over use of PSR data in maps | bar: 2021 Apr to 2021 Oct
Innovation project to add ONS and licenced data on demographics to further support planning | bar: 2021 Apr to 2022 Apr
Build analytic tools to use the data and drive communciation plans and target projects and campaigns | bar: 2021 Apr to 2022 Apr
8. National map | Actively participate in ENA subgroup PoC | bar: 2021 Jan to 2021 Dec
Develop system to seemlessly publish data to the national map | bar: 2021 Oct to 2022 Mar
Productionalise national map and increase data sets available | bar: 2022 Apr to 2022 Dec
9. Create a dedicated data and analytics team | GD2 Business restructure | bar: 2021 Jan to 2021 Mar
Populate data and analytics team | bar: 2021 Apr to 2021 Sep
Implement new data triage process | bar: 2021 Jul to 2021 Sep
Publish methods for external stakeholders to engage | bar: 2021 Oct
10. Sharing future data sets | Gas goes green - green gas data reporting through ENA | bar: 2021 Jun; 2021 Dec; 2022 Jun; 2022 Nov
Publish detailed environmental performance data | bar: 2021 Jun to 2021 Aug; 2022 Jun to 2022 Aug
Publish heat and hot water ready reckoner | bar: 2021 Apr to 2021 May